## Instructions
User Guide for Residential Roofing Integrated Photovoltaics Public Data
The data file includes field observations of residential roofing integrated photovoltaics installation that happened between July 2021 and June 2022 in California. There are 21 observations - 2 in the re-roofing category and 19 in the new construction category. The file includes two time and motion forms (Re-Roofing & New Construction) we used to capture the time it takes for each activity in the rooftop solar and electrical installation process. You will see the duration for detailed steps along with activities that are included for total installation time for the paper. There are three parts to the time and motion form - Part 1 has project and crew characteristics, product information, and inspection and permitting data and can be filled before the installation. Part 2 has the actual installation time stamps and related notes. Part 3 has the crew information and can be filled on-site or off-site, but this section is optional. The re-roofing form has pre-solar activities and gutters and vents section in Part 2 of the form, whereas new construction form includes a section for capturing the time it took for rough wiring. The re-roofing form does not include rough wiring but instead includes the final electrical wiring process. These are the key differences in both the forms. Each day/step/installation activity needs to include the crew break time as they happen and there is space available to capture the crew breaks duration. In Table 1 below, the different terms used in the time and motion form are defined and their corresponding unit of measurement stated. We also highlight the optional sections. The data is captured in total mins, total hours, person mins, person hours. You can use this form or make edits to the form to recreate the study or make your own observations.
The data herein was reviewed but may not be comprehensive. NREL invites questions and inputs to improve the data, including to: - Correct erroneous information - Fill in missing/updated information - Clarifications on data and variables Updated information may be submitted to Sushmita Jena at sushmita.jena@nrel.gov.
Table 1.
Variable Name | Definition | Units
Breaks | Lunch breaks or any other breaks crew took during installation | Minutes
Building Floors | Number of floors in the building | Number
Crew Size (Solar) | Number of people working on installation | Number
Date | The date/s of installation | Date
Gutters & Vents | Duration it took to install the gutters and vents | Minutes
Installer | Identity of the installer | Installer indentifier
Mins | Duration in minutes it took for each activity or group of activities | Minutes
Module Area Square Feet | Area of the roof opccupied by the solar modules/shingles | Square feet
Mounting Planes | Number of roof planes where solar is installed | Number
Number of modules | Number of modules/shingles used for the solar system | Number
Observed/Partial | If NREL researchers observed an installation from start to finish it is marked as observed else partial | Categorical
Person mins | Duration in minutes it took for each activity or group of activities over the number of people involved in that activity | Minutes
Phase | Applicable to new construction only. This products is installed in two phases to make a complete system - Phase 1 and Phase 2 | Name
Pre-solar Activity | Time it takes for activities done on the roof before the solar installation such as Roof tear-off, roof preparation, and roof inspection | Minutes
Product | Product Identity | Product indentifier
Rectangle | For new construction, we denote whether the installation was a rectangular shape or not | Boolean
Roof Pitch | Steepness of a roof expressed as a ratio of inch rise per horizontal foot, or as the angle in degrees its surface deviates from the horizontal | Ratio
Roof Planes | Total number of roof planes | Number
Roof Square Foot | Total square footage of the roof | Square feet
Roofing Material | Type of roofing material used for the non-solar part of the roof | Name
Roofing material obstructing work area - Yes/No | Whether roofing material obstructing the solar installation work area or not | Boolean
Site | Name of the area/community where installation took place | Name
Sl. No. | Serial Number | Number
Sub Arrays | Number of sub-arrays on different mounting planes that make up the complete system | Number
System Size (KW) | The size/capacity of the photovolataic system | Kilowatt
Temperature (F) | The average temperature during the installation period | Fahrenheit

## Re-Roofing
Re-roof
Project Characteristics | [15 empty] | Duration in mins | [6 empty] | Duration person mins
Site | Date | Region | Installer | Crew Size (Solar) | Temperature (F) | System Size (KW) | Roof Pitch | Roof Planes | Mounting Planes | No. of modules | Roof Sq Ft. | Building floors | Sub arrays | Product | Roofing Material | Step 1 (Staging & Unloading) | Step 2 (Fire Proofing & Underlayment) | Step 3 (Flashings & PV Installation) | Step 4 (Wiring & Monitoring) | Pre-solar activity | Gutters & Vents | Breaks | Step 1 (Staging & Unloading) person mins | Step 2 (Fire Proofing & Underlayment) person mins | Step 3 (Flashings & PV Installation) | Step 4 (Wiring & Monitoring) | Pre-solar activity | Gutters & Vents person mins (We were able to observe the gutters and vents only and could not complete the others) | Breaks
Site 1 | 2021-07-01 | San Rafael, CA | Installer A | 2 to 5 | 55 - 83 | 6.48 | <4/12 | 8 | 3 | 18 | 226.59 | 1 | 3 | Product A | Comp shingle | 75 | 160 | 660 | 420 | 825 | 150 | 272 | 225 | 480 | 1440 | 420 | 2985 | 150 | 674.75
Site 2 | 2022-06-01 | San Rafael, CA | Installer A | 2 to 5 | 55-100 | 14.04 | 4.5/12 | 7 | 7 | 312 | 597 | 1 | 11 | Product B | Comp shingle | 163 | 100 | 260 | 1460 | 771 | 540 | 495 | 326 | 300 | 513 | 4055 | 2590 | 1800 | 1960

## New Construction
New Construction | [17 empty] | Actual Observed Data | [5 empty] | Estimated |  |  | Actual + Estimated in total mins | [5 empty] | Actual + Estimate in Person mins
Project Charateristics | [17 empty] | Duration in mins | [8 empty] | Duration in person mins | [5 empty] | Duration in person mins
Sl. No. | Date | Area | Installer | Crew Size | Temp F | System Size kW | Module Area sqft/Size | Roof Pitch | Roof Planes | No. of modules | Building Floors | Sub arrays | Rectangle | Product | Observed/Partial | Roofing material obstructing work area - Yes/No | Roofing Material | Step 1 (Staging & Unloading) in mins | Step 2 (Fire Proofing & Underlayment) in mins | Step 3 (Flashings & PV Installation) in mins | Step 4 (Wiring & Monitoring) in mins | Lunch break | Total without lunch break | Estimation methods | Day 1 time estimated or NA in mins (day wise) | Day 2 time estimated or NA in mins (day wise) | Step 1 (Staging & Unloading) person mins | Step 2 (Fire Proofing & Underlayment) person mins | Step 3 (Flashings & PV Installation) person mins | Step 4 (Wiring & Monitoring) person mins | Lunch break in person mins | Total Actual +Estimated in mins without Lunch break | Step 1 (Staging & Unloading) person mins | Step 2 (Fire Proofing & Underlayment) person mins | Step 3 (Flashings & PV Installation) person mins | Step 4 (Wiring & Monitoring) person mins | Lunch break in person mins | Total without lunch break
1 | 2021-08-16 | Roseville, CA | Installer A | 2 | 100 F | 4.2 | 215 | 6:12 | 2 | 12 | 2 | 2 | No | Phase 1/Rough | Observed | Yes | Flat tile | 47 | 16 | 194 | 73 | 65 | 330 | Adding time: Should be average of observed time from similar projects: 13; 14; and 15 | NA | 128.3333 | 83 | 16 | 275 | 84.3333 | 82 | 458.3333 | 148 | 32 | 509.5 | 163 | 155.5 | 852.5
2 | 2021-08-16 | Manteca, CA | Installer B | 5 | 100 F | 3.5 | 179 | 5:12 | 1 | 10 | 2 | 1 | No | Phase 1/Rough | Partial | No | Flat tile | 26 | 14 | 103 | 46 | 30 | 189 | Based on project 12, modules are similar, floors don’t really matter. | NA | 160 | 63 | 14 | 203 | 69 | 47 | 349 | 185.5 | 70 | 665 | 264.5 | 184.5 | 1185
3 | 2021-08-16 | Manteca, CA | Installer B | 5 | 100 F | 3.15 | 161 | 5:12 | 1 | 9 | 2 | 1 | Yes | Phase 1/Rough | Partial | No | Flat tile | 29 | 10 | 60 | 55 | 30 | 154 | Based on project 12. | NA | 160 | 66 | 10 | 160 | 78 | 47 | 314 | 200.5 | 50 | 450 | 309.5 | 184.5 | 1010
4 | 2021-08-17 | Manteca, CA | Installer B | 3 | 89 F | 4.2 | 215 | 4:12 | 1 | 12 | 2 | 1 | No | Phase 1/Rough | Observed | Yes | Flat tile | 29 | 10 | 60 | 40 | 35 | 139 | Based on project 12. | NA | 160 | 66 | 10 | 160 | 63 | 52 | 299 | 142.5 | 30 | 330 | 154.5 | 139.5 | 657
5 | 2021-08-17 | Manteca, CA | Installer B | 3 | 89 F | 3.85 | 197 | 4:12 | 1 | 11 | 1 | 1 | No | Phase 1/Rough | Observed | Yes | Flat tile | 29 | 10 | 55 | 40 | 30 | 134 | Based on project 12. | NA | 160 | 66 | 10 | 155 | 63 | 47 | 294 | 142.5 | 30 | 315 | 154.5 | 124.5 | 642
6 | 2021-08-17 | Manteca, CA | Installer B | 3 | 79 F | 3.15 | 161 | 5:12 | 1 | 9 | 1 | 1 | No | Phase 1/Rough | Partial | No | Flat tile | 29 | 30 | 50 | 65 | 20 | 174 | Based on project 12. | NA | 160 | 66 | 30 | 150 | 88 | 37 | 334 | 142.5 | 90 | 300 | 229.5 | 94.5 | 762
7 | 2021-08-17 | Manteca, CA | Installer B | 3 | 76 F | 3.5 | 179 | 5:12 | 1 | 10 | 2 | 1 | Yes | Phase 1/Rough | Partial | No | Flat tile | 12 | 12 | 50 | 35 | 20 | 109 | Based on project 12. | NA | 160 | 49 | 12 | 150 | 58 | 37 | 269 | 91.5 | 36 | 300 | 139.5 | 94.5 | 567
8 | 2021-08-17 | Manteca, CA | Installer B | 3 | 73 F | 3.5 | 179 | 5:12 | 1 | 10 | 2 | 1 | Yes | Phase 1/Rough | Partial | No | Flat tile | 29 | 10 | 59 | 50 | 20 | 148 | Based on project 12. | NA | 160 | 66 | 10 | 159 | 73 | 37 | 308 | 142.5 | 30 | 327 | 219 | 94.5 | 718.5
9 | 2021-08-18 | Manteca, CA | Installer B | 4 | 77 F | 3.5 | 179 | 5:12 | 1 | 10 | 2 | 1 | Yes | Phase 1/Rough | Observed | Yes | Flat tile | 29 | 10 | 59 | 50 | 20 | 148 | Based on project 12. | NA | 160 | 66 | 10 | 159 | 73 | 37 | 308 | 171.5 | 40 | 386 | 269 | 114.5 | 866.5
10 | 2021-08-18 | Manteca, CA | Installer B | 4 | 77 F | 3.5 | 179 | 5:12 | 1 | 10 | 2 | 1 | Yes | Phase 1/Rough | Observed | Yes | Flat tile | 29 | 10 | 59 | 50 | 20 | 148 | Based on project 12. | NA | 160 | 66 | 10 | 159 | 73 | 37 | 308 | 171.5 | 40 | 386 | 200 | 114.5 | 797.5
11 | 2021-08-18 | Manteca, CA | Installer B | 4 | 77 F | 3.15 | 161 | 5:12 | 1 | 9 | 1 | 1 | No | Phase 1/Rough | Observed | Yes | Flat tile | 45 | 13 | 94 | 46 | 30 | 198 | Based on project 12. | NA | 160 | 82 | 13 | 194 | 69 | 47 | 358 | 235.5 | 52 | 526 | 184 | 154.5 | 997.5
12 | 2021-08-19 | Fairfield, CA | Installer C | 1.5 | 71 F | 3.85 | 197 | 4:12 | 1 | 11 | 2 | 1 | No | Phase 2 | Observed | No | Flat tile | 37 |  | 100 | 23 | 17 | 160 | Average of project 2, 4, and 19 (and any others missing) | 172.6667 | NA
13 | 2021-08-19 | Fairfield, CA | Installer C | 1.5 | 71 F | 4.2 | 215 | 4.5:12 | 2 | 12 | 2 | 2 | No | Phase 2 | Observed | No | Flat tile | 36 |  | 100 | 12 | 17 | 148 | Average based on project 1 and 18 | 234.5 | NA
14 | 2021-08-19 | Fairfield, CA | Installer C | 1.5 | 84 F | 3.85 | 197 | 4:12 | 2 | 11 | 2 | 2 | No | Phase 2 | Observed | No | Flat tile | 54 |  | 63 | 8 | 17 | 125 | Average based on project 1 and 18 | 234.5 | NA
15 | 2021-08-19 | Fairfield, CA | Installer C | 1.5 | 84 F | 3.85 | 197 | 4:12 | 2 | 11 | 2 | 2 | No | Phase 2 | Observed | No | Flat tile | 18 |  | 80 | 14 | 17 | 112 | Average based on project 1 and 18 | 234.5 | NA
16 | 2021-08-19 | Fairfield, CA | Installer C | 1.5 | 84 F | 4.55 | 233 | 4:12 | 3 | 13 | 2 | 3 | No | Phase 2 | Partial | No | Flat tile | 37 |  | 130 | 14 | 20 | 181 | Average of project 1 and 18+ the average of 2nd array being added. | 356.5 | NA
17 | 2021-08-19 | Fairfield, CA | Installer C | 1.5 | 84 F | 4.55 | 233 | 4:12 | 3 | 13 | 2 | 3 | No | Phase 2 | Partial | No | Flat tile | 37 |  | 130 | 14 | 20 | 181 | Average of project 1 and 18+ the average of 2nd array being added. | 356.5 | NA
18 | 2021-08-20 | Roseville, CA | Installer A | 3 | 66 F | 3.85 | 197 | 4:12 | 2 | 11 | 2 | 2 | No | Phase 1/Rough | Observed | No | Flat tile | 34 | 7 | 58 | 40 | 40 | 139 | Adding time: Should be average of observed time from similar projects: 13; 14; and 15 | NA | 128.3333 | 70 | 7 | 139 | 51.3333 | 57 | 267.3333 | 156 | 21 | 295.5 | 137 | 145.5 | 609.5
19 | 2021-08-20 | Roseville, CA | Installer A | 3 | 73 F | 3.85 | 197 | 4:12 | 1 | 11 | 2 | 1 | No | Phase 1/Rough | Partial | No | Flat tile | 70 | 16 | 64 | 40 | 30 | 190 | Based on project 12. | NA | 160 | 107 | 16 | 164 | 63 | 47 | 350 | 265.5 | 48 | 342 | 120 | 124.5 | 775.5
[17 empty] | Avg in mins | 34.5263 | 12.9231 | 82.5263 | 37.6316 | 26.2105 | 163.5263 |  |  |  | 70.4615 | 12.9231 | 171.3077 | 69.6667 |  | 324.359 | 168.8846 | 43.7692 | 394.7692 | 195.6923 | 132.7308 | 803.1154
[17 empty] | Avg in hours | 0.57544 | 0.21538 | 1.3754 | 0.62719 | 0.43684 | 2.7254 |  |  |  | 1.1744 | 0.21538 | 2.8551 | 1.1611 |  | 5.406 | 2.8147 | 0.72949 | 6.5795 | 3.2615 | 2.2122 | 13.3853

## Time & Motion Form - Re-Roofing
The data file includes field observations of residential roofing integrated photovoltaics installation that happened between July 2021 and June 2022 in California. There are 21 observations - 2 in the re-roofing category and 19 in the new construction category. The file includes two time and motion forms (Re-Roofing & New Construction) we used to capture the time it takes for each activity in the rooftop solar and electrical installation process. You will see the duration for detailed steps along with activities that are included for total installation time for the paper. There are three parts to the time and motion form - Part 1 has project and crew characteristics, product information, and inspection and permitting data and can be filled before the installation. Part 2 has the actual installation time stamps and related notes. Part 3 has the crew information and can be filled on-site or off-site, but this section is optional. The re-roofing form has pre-solar activities and gutters and vents section in Part 2 of the form, whereas new construction form includes a section for capturing the time it took for rough wiring. The re-roofing form does not include rough wiring but instead includes the final electrical wiring process. These are the key differences in both the forms. Each day/step/installation activity needs to include the crew break time as they happen and there is space available to capture the crew breaks duration. In Table 1 below, the different terms used in the time and motion form are defined and their corresponding unit of measurement stated. We also highlight the optional sections. The data is captured in total mins, total hours, person mins, person hours. You can use this form or make edits to the form to recreate the study or make your own observations.
The data herein was reviewed but may not be comprehensive. NREL invites questions and inputs to improve the data, including to: - Correct erroneous information - Fill in missing/updated information - Clarifications on data and variables Updated information may be submitted to Sushmita Jena at sushmita.jena@nrel.gov.
Variable Name | Definition | Units
Breaks | Lunch breaks or any other breaks crew took during installation | Minutes
Building Floors | Number of floors in the building | Number
Crew Size (Solar) | Number of people working on installation | Number
Date | The date/s of installation | Date
Gutters & Vents | Duration it took to install the gutters and vents | Minutes
Installer | Identity of the installer | Installer indentifier
Mins | Duration in minutes it took for each activity or group of activities | Minutes
Module Area Square Feet | Area of the roof opccupied by the solar modules/shingles | Square feet
Mounting Planes | Number of roof planes where solar is installed | Number
Number of modules | Number of modules/shingles used for the solar system | Number
Observed/Partial | If NREL researchers observed an installation from start to finish it is marked as observed else partial | Categorical
Person mins | Duration in minutes it took for each activity or group of activities over the number of people involved in that activity | Minutes
Phase | Applicable to new construction only. This products is installed in two phases to make a complete system - Phase 1 and Phase 2 | Name
Pre-solar Activity | Time it takes for activities done on the roof before the solar installation such as Roof tear-off, roof preparation, and roof inspection | Minutes
Product | Product Identity | Product indentifier
Rectangle | For new construction, we denote whether the installation was a rectangular shape or not | Boolean
Roof Pitch | Steepness of a roof expressed as a ratio of inch rise per horizontal foot, or as the angle in degrees its surface deviates from the horizontal | Ratio
Roof Planes | Total number of roof planes | Number
Roof Square Foot | Total square footage of the roof | Square feet
Roofing Material | Type of roofing material used for the non-solar part of the roof | Name
Roofing material obstructing work area - Yes/No | Whether roofing material obstructing the solar installation work area or not | Boolean
Site | Name of the area/community where installation took place | Name
Sl. No. | Serial Number | Number
Sub Arrays | Number of sub-arrays on different mounting planes that make up the complete system | Number
System Size (KW) | The size/capacity of the photovolataic system | Kilowatt
Temperature (F) | The average temperature during the installation period | Fahrenheit
Time & Motion Form - Re-Roofing
Part 1
Pre installation form/Offsite form
Project and Crew Characteristics
Time study # (Unique identifier) | Product ID | Installation date | Crew Size | Number of training hours in solar generally (for individual member of the crew) | Training in the product being installed | If you have been trained in the specific product, how many installations of the specific product have you done?
Information that can be filled beforehand |  |  |  | (x+y)/n = average number of hours of training of crew | Name of the Original Equipment Manufacturer, hours of training | Number of installations
Crew
Crew Size | Does the installer operate in multiple states? | What licenses does installer/roofer have? | For how many years he/she/roofer has had the above license? | Is the primary team a roofer or a solar team? | How many projects have you done in this AHJ as an installer?
Number of individuals | If yes, please list states | Name of the License/Type of the License | Number of years | Roofer/Solar | Number of installations
Product Design
System size | Install Cost | Product/Manufacturer Name | Model Name | Module Configuration | Number of Modules | Module size | Watts per module | Level of customization (Did you have to do as built changes to the system design?( 1-5) | Roof Pitch | Number of sub-arrays | Building floors | Number of components in product | Weather | What is the weight of the system? Is it greater than 3 PSF? | Roofing Material | How many roof planes include solar? | Electrical Tie-in Method | What is conduit run length? | Is the conduit run internally or externally?
Watts | Dollar Value | Name | Name of the OEM | Array shape and rows | Number of modules | Meter square | Number | 1 – 5 scale* (Qualitative description justifying customization ranking ) | Degrees | Rows or shapes | Number | Number of components to be installed | Temperature (°C/°F), Precipitation (%), and Humidity (%) | Weights + Greater or less that 3 PSF | Name of the material | Name | Length | Internal or External | In hours
Inspection & permitting
How long did system design take? | How long did it take to get the permit? | Were there as-built changes required, if yes, describe? | Did you need approval to build from the electric service provider? | If required, how long did it take to get approval to build from the electric service provider | Does the permitting authority require a rough inspection? | When was the 1st rough inspection done? | What was the result of rough inspection? | When was the final inspection done? | What was the result of the final inspection? If failed why | Where was the material staged and how was it transported to the roof? | Collect a copy of the planset
In days | In days | Yes/No and qualitative description | Yes/No | In days | Yes/No | Date | Pass/Fail, and qualitative description | Date | Pass/Fail, and qualitative description | Location | Copy the planset
Part 2
On-site/Field form
Pre-Solar Activity
Time study # (Unique identifier) | Roof tear-off | Travel |  |  | NOTES (Any thing out of the ordinary that happened) | Roof inspection |  |  | NOTES (Any thing out of the ordinary that happened) | Wood/non-solar material delivery |  |  | NOTES (Any thing out of the ordinary that happened) | Roof Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
|  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Pre-Solar Activity
Gutters & Vents
Time study # (Unique identifier) | Gutters | Travel |  |  | NOTES (Any thing out of the ordinary that happened) | Vents |  |  | NOTES (Any thing out of the ordinary that happened) | Painting |  |  | NOTES (Any thing out of the ordinary that happened) | Small handyman |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
|  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Non-Solar Activity
Mounting Plane 1
Step 1 - Staging & Unloading, and Roof Prep
Time study # (Unique identifier) | Coordinate/Pre-install office prep - describe qualitatively | Travel |  |  | NOTES (Any thing out of the ordinary that happened) | Unload on the site |  |  | NOTES (Any thing out of the ordinary that happened) | Unpack on the roof |  |  | NOTES (Any thing out of the ordinary that happened) | Roof Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
|  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 1
Step 2 - Fire Proofing & Underlayment
Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Position as per project design |  |  | NOTES (Any thing out of the ordinary that happened) | Fire Proofing |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 2
Step 3 - Flashings Installation
Attach Flashings |  |  | NOTES (Any thing out of the ordinary that happened) | Install |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 3
Step - 4 - PV Install Date/Time:
Step 4 -Flashings & PV Installation | Date/Time |  | NOTES (Any thing out of the ordinary that happened) | Wiring |  |  | NOTES (Any thing out of the ordinary that happened) | Quality Assurance |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Total | Start | End |  | Start | End | Total |  | Total time for Step 4
Mounting Plane 2
Step 1 - Staging & Unloading, and Roof Prep
Time study # (Unique identifier) | Coordinate/Pre-install office prep - describe qualitatively | Travel |  |  | NOTES (Any thing out of the ordinary that happened) | Unload on the site |  |  | NOTES (Any thing out of the ordinary that happened) | Unpack on the roof |  |  | NOTES (Any thing out of the ordinary that happened) | Roof Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
|  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 1
Step 2 - Fire Proofing & Underlayment
Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Position as per project design |  |  | NOTES (Any thing out of the ordinary that happened) | Fire Proofing |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 2
Step 3 - Flashings Installation
Attach Flashings |  |  | NOTES (Any thing out of the ordinary that happened) | Install |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 3
Step 4 -Flashings & PV Installation | Date/Time
PV Install |  |  | NOTES (Any thing out of the ordinary that happened) | Wiring |  |  | NOTES (Any thing out of the ordinary that happened) | Quality Assurance |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Total | Start | End |  | Start | End | Total |  | Total time for Step 4
Mounting Plane 3
Step 1 - Staging & Unloading, and Roof Prep | Mounting Plane 3
Time study # (Unique identifier) | Coordinate/Pre-install office prep - describe qualitatively | Travel |  |  | NOTES (Any thing out of the ordinary that happened) | Unload on the site |  |  | NOTES (Any thing out of the ordinary that happened) | Unpack on the roof |  |  | NOTES (Any thing out of the ordinary that happened) | Roof Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
|  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 1
Step 2 - Fire Proofing & Underlayment
Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Position as per project design |  |  | NOTES (Any thing out of the ordinary that happened) | Fire Proofing |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 2
Step 3 - Flashings Installation
Attach Flashings |  |  | NOTES (Any thing out of the ordinary that happened) | Install |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 3
Step 4 -Flashings & PV Installation | Date/Time
PV Install |  |  | NOTES (Any thing out of the ordinary that happened) | Wiring |  |  | NOTES (Any thing out of the ordinary that happened) | Quality Assurance |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Total | Start | End |  | Start | End | Total |  | Total time for Step 4
Mounting plane n (If there are more Mounting Planes, please repeat the above steps here )
Total installation time in mins
Total
Part 3 (optional)
Crew information - Onsite/Offsite form
Time study # (Unique identifier) | What are the names of the crew members? | List the specific tasks you are performing during installation | How long have you been a part of this company and crew? | How many similar installs have you done? | Have you received training in this product? | Do you think you have adequte training to do the job? | Would you like more training in solar installation? | Do you have a second job? | Crew Lead | Crew Members Names (in full)
Answers

## Time & Motion Form - New cons
The data file includes field observations of residential roofing integrated photovoltaics installation that happened between July 2021 and June 2022 in California. There are 21 observations - 2 in the re-roofing category and 19 in the new construction category. The file includes two time and motion forms (Re-Roofing & New Construction) we used to capture the time it takes for each activity in the rooftop solar and electrical installation process. You will see the duration for detailed steps along with activities that are included for total installation time for the paper. There are three parts to the time and motion form - Part 1 has project and crew characteristics, product information, and inspection and permitting data and can be filled before the installation. Part 2 has the actual installation time stamps and related notes. Part 3 has the crew information and can be filled on-site or off-site, but this section is optional. The re-roofing form has pre-solar activities and gutters and vents section in Part 2 of the form, whereas new construction form includes a section for capturing the time it took for rough wiring. The re-roofing form does not include rough wiring but instead includes the final electrical wiring process. These are the key differences in both the forms. Each day/step/installation activity needs to include the crew break time as they happen and there is space available to capture the crew breaks duration. In Table 1 below, the different terms used in the time and motion form are defined and their corresponding unit of measurement stated. We also highlight the optional sections. The data is captured in total mins, total hours, person mins, person hours. You can use this form or make edits to the form to recreate the study or make your own observations.
The data herein was reviewed but may not be comprehensive. NREL invites questions and inputs to improve the data, including to: - Correct erroneous information - Fill in missing/updated information - Clarifications on data and variables Updated information may be submitted to Sushmita Jena at sushmita.jena@nrel.gov.
Variable Name | Definition | Units
Breaks | Lunch breaks or any other breaks crew took during installation | Minutes
Building Floors | Number of floors in the building | Number
Crew Size (Solar) | Number of people working on installation | Number
Date | The date/s of installation | Date
Gutters & Vents | Duration it took to install the gutters and vents | Minutes
Installer | Identity of the installer | Installer indentifier
Mins | Duration in minutes it took for each activity or group of activities | Minutes
Module Area Square Feet | Area of the roof opccupied by the solar modules/shingles | Square feet
Mounting Planes | Number of roof planes where solar is installed | Number
Number of modules | Number of modules/shingles used for the solar system | Number
Observed/Partial | If NREL researchers observed an installation from start to finish it is marked as observed else partial | Categorical
Person mins | Duration in minutes it took for each activity or group of activities over the number of people involved in that activity | Minutes
Phase | Applicable to new construction only. This products is installed in two phases to make a complete system - Phase 1 and Phase 2 | Name
Pre-solar Activity | Time it takes for activities done on the roof before the solar installation such as Roof tear-off, roof preparation, and roof inspection | Minutes
Product | Product Identity | Product indentifier
Rectangle | For new construction, we denote whether the installation was a rectangular shape or not | Boolean
Roof Pitch | Steepness of a roof expressed as a ratio of inch rise per horizontal foot, or as the angle in degrees its surface deviates from the horizontal | Ratio
Roof Planes | Total number of roof planes | Number
Roof Square Foot | Total square footage of the roof | Square feet
Roofing Material | Type of roofing material used for the non-solar part of the roof | Name
Roofing material obstructing work area - Yes/No | Whether roofing material obstructing the solar installation work area or not | Boolean
Site | Name of the area/community where installation took place | Name
Sl. No. | Serial Number | Number
Sub Arrays | Number of sub-arrays on different mounting planes that make up the complete system | Number
System Size (KW) | The size/capacity of the photovolataic system | Kilowatt
Temperature (F) | The average temperature during the installation period | Fahrenheit
Time & Motion Form - New Construction
Part 1
Pre installation form/Offsite form
Project and Crew Characteristics
Time study # (Unique identifier) | Product ID | Installation date | Crew Size | Number of training hours in solar generally (for individual member of the crew) | Training in the product being installed | If you have been trained in the specific product, how many installations of the specific product have you done?
Information that can be filled beforehand |  |  |  | (x+y)/n = average number of hours of training of crew | Name of the Original Equipment Manufacturer, hours of training | Number of installations
Crew
Crew Size | Does the installer operate in multiple states? | What licenses does installer/roofer have? | For how many years he/she/roofer has had the above license? | Is the primary team a roofer or a solar team? | How many projects have you done in this AHJ as an installer?
Number of individuals | If yes, please list states | Name of the License/Type of the License | Number of years | Roofer/Solar | Number of installations
Product Design
System size | Install Cost | Product/Manufacturer Name | Model Name | Module Configuration | Number of Modules | Module size | Watts per module | Level of customization (Did you have to do as built changes to the system design?( 1-5) | Roof Pitch | Number of sub-arrays | Building floors | Number of components in product | Weather | What is the weight of the system? Is it greater than 3 PSF? | Roofing Material | How many roof planes include solar? | Electrical Tie-in Method | What is conduit run length? | Is the conduit run internally or externally?
Watts | Dollar Value | Name | Name of the OEM | Array shape and rows | Number of modules | Meter square | Number | 1 – 5 scale* (Qualitative description justifying customization ranking ) | Degrees | Rows or shapes | Number | Number of components to be installed | Temperature (°C/°F), Precipitation (%), and Humidity (%) | Weights + Greater or less that 3 PSF | Name of the material | Name | Length | Internal or External | In hours
Inspection & permitting
How long did system design take? | How long did it take to get the permit? | Were there as-built changes required, if yes, describe? | Did you need approval to build from the electric service provider? | If required, how long did it take to get approval to build from the electric service provider | Does the permitting authority require a rough inspection? | When was the 1st rough inspection done? | What was the result of rough inspection? | When was the final inspection done? | What was the result of the final inspection? If failed why | Where was the material staged and how was it transported to the roof? | Collect a copy of the planset
In days | In days | Yes/No and qualitative description | Yes/No | In days | Yes/No | Date | Pass/Fail, and qualitative description | Date | Pass/Fail, and qualitative description | Location | Copy the planset
Part 2
On-site/Field form
Rough Wiring
Rough Wiring | Rough Wiring |  |  | NOTES | Rough Wiring monitoring |  |  | NOTES | Breaks |  |  | NOTES
Time study # (Unique identifier) | Start | End | Total |  | Start | End | Total |  | Start | End | Total
Mounting Plane 1
Step 1 - Staging & Unloading, and Roof Prep
Time study # (Unique identifier) | Coordinate/Pre-install office prep - describe qualitatively | Travel |  |  | NOTES (Any thing out of the ordinary that happened) | Unload on the site |  |  | NOTES (Any thing out of the ordinary that happened) | Unpack on the roof |  |  | NOTES (Any thing out of the ordinary that happened) | Roof Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
|  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 1
Step 2 - Fire Proofing & Underlayment
Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Position as per project design |  |  | NOTES (Any thing out of the ordinary that happened) | Fire Proofing |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 2
Step 3 - Flashings Installation
Attach Flashings |  |  | NOTES (Any thing out of the ordinary that happened) | Install |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 3
Step - 4 - PV Install Date/Time:
Step 4 -Flashings & PV Installation | Date/Time |  | NOTES (Any thing out of the ordinary that happened) | Wiring |  |  | NOTES (Any thing out of the ordinary that happened) | Quality Assurance |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Total | Start | End |  | Start | End | Total |  | Total time for Step 4
Mounting Plane 2
Step 1 - Staging & Unloading, and Roof Prep
Time study # (Unique identifier) | Coordinate/Pre-install office prep - describe qualitatively | Travel |  |  | NOTES (Any thing out of the ordinary that happened) | Unload on the site |  |  | NOTES (Any thing out of the ordinary that happened) | Unpack on the roof |  |  | NOTES (Any thing out of the ordinary that happened) | Roof Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
|  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 1
Step 2 - Fire Proofing & Underlayment
Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Position as per project design |  |  | NOTES (Any thing out of the ordinary that happened) | Fire Proofing |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 2
Step 3 - Flashings Installation
Attach Flashings |  |  | NOTES (Any thing out of the ordinary that happened) | Install |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 3
Step 4 -Flashings & PV Installation | Date/Time
PV Install |  |  | NOTES (Any thing out of the ordinary that happened) | Wiring |  |  | NOTES (Any thing out of the ordinary that happened) | Quality Assurance |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Total | Start | End |  | Start | End | Total |  | Total time for Step 4
Mounting Plane 3
Step 1 - Staging & Unloading, and Roof Prep | Mounting Plane 3
Time study # (Unique identifier) | Coordinate/Pre-install office prep - describe qualitatively | Travel |  |  | NOTES (Any thing out of the ordinary that happened) | Unload on the site |  |  | NOTES (Any thing out of the ordinary that happened) | Unpack on the roof |  |  | NOTES (Any thing out of the ordinary that happened) | Roof Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
|  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 1
Step 2 - Fire Proofing & Underlayment
Preparation |  |  | NOTES (Any thing out of the ordinary that happened) | Position as per project design |  |  | NOTES (Any thing out of the ordinary that happened) | Fire Proofing |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 2
Step 3 - Flashings Installation
Attach Flashings |  |  | NOTES (Any thing out of the ordinary that happened) | Install |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Start | End | Total |  | Total time for Step 3
Step 4 -Flashings & PV Installation | Date/Time
PV Install |  |  | NOTES (Any thing out of the ordinary that happened) | Wiring |  |  | NOTES (Any thing out of the ordinary that happened) | Quality Assurance |  |  | NOTES (Any thing out of the ordinary that happened) | Breaks |  |  | NOTES
Start | End | Total |  | Start | End | Total |  | Total | Start | End |  | Start | End | Total |  | Total time for Step 4
Mounting plane n (If there are more Mounting Planes, please repeat the above steps here )
Total installation time in mins
Total
Part 3 (optional)
Crew information - Onsite/Offsite form
Time study # (Unique identifier) | What are the names of the crew members? | List the specific tasks you are performing during installation | How long have you been a part of this company and crew? | How many similar installs have you done? | Have you received training in this product? | Do you think you have adequte training to do the job? | Would you like more training in solar installation? | Do you have a second job? | Crew Lead | Crew Members Names (in full)
Answers